## Sheet1
Phase | Category | Activity/Tasks | Module | Sub-Tasks | Planned start date | Planned End Date | Planned Effort | Responsibility | Actual Effort | Actual Start End | Actual End Date | Schedule Variance | Effort Variance | Reason For Deviation | Action Plan | Remarks | Status
Phase 1 | Analysis
| Coding | Issues & client changes | otp | auto tab input when one field is filled (tap to next) | 25/02/2019 | 25/02/2019 | 2 hrs | sajal | 2 hrs | 25/02/2019 | 25/02/2019 | 0 | 0 |  |  |  | Done
|  | Issues & client changes | no product div on product list | api hit response is slow so it shows no product div first | 28/02/2019 | 28/02/2019 | 2hrs | sajal | 2 hrs | 28/02/2019 | 28/02/2019 | 0 | 0 |  |  |  | Done
|  | client Demand | brands footer on the bottom of the homepage | brand filter slider on home page auto slide api hit + webservice function | 28/02/2019 | 29/02/2019 | 10hrs | sajal | 7hrs | 28/02/2019 | 28/02/2019 | 0 | -0.5 |  |  |  | Done